## Project Settings
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Javier Mesa
Start Date | abr 08, 2017 05:54:28 PM
Completion Date | abr 09, 2017 02:15:17 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:49 PM el 10/04/2017

## Overall Metrics
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 26.9 | 28.1 | 26.6
Planned Time | 0.27292 |  | 1899-12-31 03:38
Actual Tiempo |  | 0.24653 | 1899-12-31 05:28
CPI (Cost-Performance Index) |  |  | 0.94
% Reuse | 29.8% | 31.9% | 18.1%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 0 | 0 | 0
Total Defects/KLOC or equivalent | 22.7 | 12 | 20.4
Yield % | 71.4% | 100% | 75%
Code Review Rate | 551 | 285 | 452
% Appraisal COQ | 9.13% | 14.4% | 10.2%
% Failure COQ | 13.2% | 9.3% | 12.4%
COQ A/F Ratio | 0.69 | 1.55 | 0.82
PQI | 0.08 | 0.32 | 0.11
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:48 PM el 10/04/2017

## Program Size
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 134 | 134 | 745
Deleted (D) | 100 | 106 | 597
Modified (M) | 15 | 21 | 78
Added (A) | 161 | 145 | 705
Reused (R) | 83 | 81 | 188
Added and Modified (A+M) | 176 | 166 | 783
Total Size (T) | 278 | 254 | 1041
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 160 | 166 | 673
Upper Prediction Interval (70%) | 191
Lower Prediction Interval (70%) | 162
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:50 PM el 10/04/2017

## Time In Phase
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.068056 | 0.060417 | 0.30556 | 24.9%
DiseÃ±o | 0.040972 | 0.056944 | 0.20417 | 16.6%
RevisiÃ³n de DiseÃ±o | 0.011806 | 0.011111 | 0.052778 | 4.3%
CodificaciÃ³n | 0.086111 | 0.058333 | 0.36667 | 29.9%
RevisiÃ³n de CodificaciÃ³n | 0.013194 | 0.024306 | 0.072222 | 5.88%
CompilaciÃ³n | 0.019444 | 0.015278 | 0.084722 | 6.9%
Pruebas | 0.016667 | 0.0076389 | 0.068056 | 5.54%
Postmortem | 0.016667 | 0.0125 | 0.073611 | 6%
Total | 0.27292 | 0.24653 | 1899-12-31 05:28
Total Time UPI (70%) | 0.30694
Total Time LPI (70%) | 0.23889
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:50 PM el 10/04/2017

## Defects Injected
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.29 | 0 | 1 | 6.25%
DiseÃ±o | 2 | 1 | 8 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 1.71 | 1 | 7 | 43.8%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 4 | 2 | 16
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:51 PM el 10/04/2017

## Defects Removed
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.57 | 1 | 3 | 18.8%
CodificaciÃ³n | 2 | 0 | 7 | 43.8%
RevisiÃ³n de CodificaciÃ³n | 0.29 | 1 | 2 | 12.5%
CompilaciÃ³n | 1.14 | 0 | 4 | 25%
Pruebas | 0 | 0 | 0 | 0%
Total | 4 | 2 | 16
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:54 PM el 10/04/2017

## Defect Removal Efficiency
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.05 | 3.75 | 2.37
Defects/Hour - Code Review | 0.89 | 1.71 | 1.15
Defects/Hour - Compile | 2.46 | 0 | 1.97
Defects/Hour - Test | 0 | 0 | 0
DRL (DLDR/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Code Review/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Compile/UT) | #VALUE! | #DIV/0! | #DIV/0!
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:55 PM el 10/04/2017